## Slide 1
East West University | Dept. of CSE | CSE 347
StudyByte
Peer-to-Peer Micro-Tutoring Platform
Group 04 | Spring 2026
Belal Hossain · Esrat Jahan Samiya · Md. Majharul Islam · Md. Jakaria Masud
Supervisor: Dr. Hosney Jahan, Assistant Professor

## Slide 2
Introduction
Project Overview
What is StudyByte?
A web-based Peer-to-Peer Micro-Tutoring platform for university students to offer and receive topic-based tutoring through a structured digital marketplace.
🎓 Tutor Side
Submit grade report
List micro-topics & set price (tokens)
Conduct sessions & earn
📚 Learner Side
Browse marketplace by topic
Book sessions using tokens
Rate & review tutors
🔐 Platform Core
Role-based dashboards
Escrow payment protection
Admin monitoring & disputes

## Slide 3
Literature Review
Existing Platforms & Research Gap
Platform / Study | Strength | Gap Addressed by StudyByte
Chegg / Wyzant | On-demand tutoring | Not peer-driven; costly for students
Upwork (freelance) | Skill marketplace | No academic verification or escrow
MOOC (Coursera/edX) | Structured learning | No real-time peer interaction
P2P Learning Research | Proven peer learning benefits | No formal payment or trust mechanism
StudyByte | Verified peer tutors + escrow | Bridges gap for university context
Platform / Study
Strength
Gap Addressed by StudyByte
Chegg / Wyzant
On-demand tutoring
Not peer-driven; costly for students
Upwork (freelance)
Skill marketplace
No academic verification or escrow
MOOC (Coursera/edX)
Structured learning
No real-time peer interaction
P2P Learning Research
Proven peer learning benefits
No formal payment or trust mechanism
StudyByte
Verified peer tutors + escrow
Bridges gap for university context

## Slide 4
Problem Statement
Challenges in Academic Peer Learning
❌ No Trusted Peer Platform
Students lack a verified, structured space to offer or receive academic tutoring.
💸 Insecure Payments
No reliable escrow mechanism causes mistrust—tutors may not deliver after payment.
🔍 Unverified Tutor Quality
Existing informal channels have no grade verification or rating systems.
📅 Scheduling Conflicts
Manual coordination via messaging apps is unstructured and error-prone.

## Slide 5
Objectives
What StudyByte Sets Out to Achieve
01
Secure Academic Marketplace
A verified, trusted space for university peer tutoring
02
Structured Booking & Scheduling
Prevent conflicts with availability-based session booking
03
Token-Based Escrow Payment
Protect both parties—tokens held until session verified
04
Quality Assurance via Ratings
Rating & review system maintains tutor accountability
05
Admin Governance
Monitor, approve, and manage disputes platform-wide
06
Simple, Accessible Interface
Mobile-responsive UI for all university students

## Slide 6
Proposed System / Methodology
Platform Architecture & Flow
1
Register
University email + role
2
Marketplace
Browse / list topics
3
Book
Select slot & confirm
4
Escrow
Tokens held securely
5
Session
Video + code verify
6
Pay & Rate
Release tokens + review
Tech Stack
HTML / CSS / JavaScript
PHP / Python (Backend)
MySQL (Database)
bKash (Withdrawal)
Token-based Wallet
Out of Scope: Built-in video conferencing · External banking gateway · Multi-institution deployment

## Slide 7
Requirement Analysis
Functional Requirements
User Management
Register via university email
Secure login / logout
3 roles: Learner, Tutor, Admin
Separate role-based dashboards
Marketplace & Booking
Tutors list micro-topics + set price
Filter by price, rating, urgency
Availability-based scheduling
No double booking of time slots
Payment & Wallet
Token-based digital wallet
Tokens deducted on booking
Escrow holds until session ends
Release on meeting code validation
Session & Rating
Unique meeting code per session
Code submission verifies completion
Learner rates & reviews tutor
Auto-calculated average rating
Admin Control
Monitor users & transactions
Manage disputes
Approve token withdrawals
Suspend suspicious accounts
Profile Management
Update profile info
Tutors add expertise topics
Store student ID & department
Grade report verification

## Slide 8
Requirement Analysis
Non-Functional Requirements
⚡ Performance
Page load < 2 seconds
500+ concurrent users
Wallet transactions < 3 sec
🔒 Security
Role-based access control
Encrypted passwords
Only admin approves withdrawals
🔄 Reliability
99% system uptime
Escrow prevents payment loss
Daily database backups
📱 Usability
Simple, user-friendly UI
Booking in ≤ 5 steps
Clear error messages
🖥️ Operational
Modern browser support
Mobile responsive
Standard web server
💰 Feasibility
Dev cost: BDT 40–50K
Infra: BDT 60–80K
Open-source tools (BDT 0)

## Slide 9
Diagrams — Use-Case Diagram

## Slide 10
Diagrams — Sequence Diagram: Booking System

## Slide 11
Diagrams — Sequence Diagram: Payment System

## Slide 12
Diagrams — UML Class Diagram

## Slide 13
CPM — Network Diagram

## Slide 14
CPM — Float Analysis & Summary
Activity
ES
EF
LS
LF
TF
FF
CP
A
0
4
0
4
0
0
✓
B
4
7
4
7
0
0
✓
C
7
10
7
10
0
0
✓
D
10
16
10
16
0
0
✓
E
10
16
14
20
4
4
—
F
16
20
16
20
0
0
✓
G
20
30
20
30
0
0
✓
H
30
38
30
38
0
0
✓
I
38
48
38
48
0
0
✓
J
38
42
44
48
6
6
—
K
48
51
48
51
0
0
✓
L
51
54
51
54
0
0
✓
M
54
57
54
57
0
0
✓
Project Duration
57 Days
Critical Path
A→B→C→D→F→G→H→I→K→L→M
Critical Activities
11 / 13
Non-Critical
E, J

## Slide 15
PERT — Network Diagram

## Slide 16
PERT — Activity Table & Summary
O=Optimistic · M=Most Likely · P=Pessimistic · te=Expected Time
Activity
Dep
O
M
P
te
σ
A – Feasibility
—
2
4
6
4.00
0.67
B – Req. Gathering
A
1
3
5
3.00
0.67
C – Req. Analysis
B
1
3
5
3.00
0.67
D – System Design
C
4
6
10
6.33
1.00
E – Database Design
C
4
6
9
6.17
0.83
F – UI/UX
D
2
4
6
4.00
0.67
G – User Module
E,F
7
10
14
10.17
1.17
H – Booking Module
F,G,C
6
8
12
8.33
1.00
I – Wallet & Escrow
E,G,H
6
10
14
10.00
1.33
J – Rating Feature
G,H
2
4
8
4.33
1.00
K – Admin Control
I,J
2
3
4
3.00
0.33
L – Testing
All
1
3
5
3.00
0.67
M – Documentation
L
2
3
5
3.17
0.50
PERT Summary:
Expected Duration: 58 Days
Critical Path: A→B→C→D→F→G→H→I→K→L→M
Σ Variance (σ²) on CP: 8.20 days² | Std Deviation (σ): 2.86 days

## Slide 17
Feasibility Study
All dimensions confirmed feasible
Technical
✓ Feasible
HTML/CSS/JS + Python + SQLite
Standard web server sufficient
Moderate, manageable complexity
Economic
✓ Feasible
Dev: BDT 40–50K
Infra: BDT 60–80K
Open-source tools (BDT 0)
Operational
✓ Feasible
High student acceptance
Simple UI for ease of use
Ideal for university campus
Schedule
✓ Feasible
11-week phased plan
Fits within one semester
CPM confirms 57-day delivery
Legal
✓ Feasible
No data protection violations
Tokens = internal virtual currency
Complies with university policies

## Slide 18
Project Schedule
Activity Timeline (57 Days – CPM Based)
A
Feasibility Analysis
4d
B
Requirement Gathering
3d
C
Requirement Analysis
3d
D
System Design
6d
E
Database Design
6d
F
UI/UX
4d
G
User Module
10d
H
Booking Module
8d
I
Wallet & Escrow
10d
J
Rating Feature
4d
K
Admin Control
3d
L
Testing
3d
M
Documentation
3d
0
10
20
30
40
50
57
Critical Path
Non-Critical

## Slide 19
Core System Flow
End-to-End Platform Logic
1
Authentication:
University email registration · Role selection (Tutor/Learner) · Admin approval for tutors
2
Marketplace:
Tutor lists topic · Sets price (tokens) + time slots · Marketplace becomes searchable
3
Booking & Escrow:
Learner selects tutor & slot · Tokens deducted & locked in escrow · Booking confirmed
4
Session Verification:
System generates unique meeting code · Tutor submits code · Code verified → escrow released
5
Rating & Withdrawal:
Learner rates tutor · Admin reviews withdrawals · Tutors cash out via bKash

## Slide 20
Conclusion
StudyByte successfully addresses the peer tutoring gap in university environments.
Verified peer tutoring marketplace using university email authentication
Secure escrow payment protects both tutors and learners
Structured booking & scheduling eliminates manual coordination
Rating & review system ensures continuous quality improvement
Admin controls maintain platform trust and governance
Economically feasible within BDT 1.5–1.8 lakh · Delivers in 57 days
Thank You | Group 04 | CSE 347 | Spring 2026
Supervisor: Dr. Hosney Jahan | East West University, Dhaka